## Emergency Department
2027 QAPI
QAPI Project Identification
Department | Emergency Department
QAPI Category | Patient Experience/Access/Care Coordination
Project Title | LWBS
Executive Sponsor | Susan Straus
Project Lead (Name and Title) | Shelley Uhlir
Team Members | Susan Straus, Shelley Uhlir, Dr. Hill
Oversight Committee | Quality Council
Review Frequency | Monthly
Problem Statemement & Rationale
Problem Statement | Data from Year-To-Date (YTD) audits indicates that the Emergency Department's LWBS rate is currently averaging 4.2%, which exceeds the national average of <3.0%. This elevated rate compromises patient safety by delaying critical interventions, damages patient satisfaction due to excessive wait times, and causes a direct loss of revenue from untreated, unbilled patients.
Primary Rationale | Problem-prone
Measures & Baseline Data
Outcome Measure | LWBS rate
Baseline Performance | 4.2% January - August
Target/Benchmark | <3%
Data Source | CareOne Report
Data Collection Frequency | Monthly
Data Owner | Shelley Uhlir
Root Cause Analysis
Finding | The root cause of the elevated 4.2% Left Without Being Seen (LWBS) rate was extended front-end wait times and a lack of timely triage communication, which resulted from inefficient staffing alignment during peak arrival hours and bottlenecks in the initial medical evaluation process.
SMART Goal
Goal | Reduce LWBS rate from 4.2% to 3% by 12/31/2027.
Action Plan/Interventions
Action Item (Who/What/Where/When/How) | Direct Bedding: Bypass the waiting room entirely when beds are free. Move patients directly into open care spaces, even if an assigned nurse is not immediately free to start treatment.
Root Cause Addressed | Front End Throughput
Owner | Shelley Uhlir
Due Date | 2027-02-01
Status
Action Item (Who/What/Where/When/How) | Standing Orders: Enetered by charge nurse or triage RN when a patient reaches 30 minute wait in triage.
Root Cause Addressed | Front End Throughput
Owner | Shelley Uhlir
Due Date | 2027-02-01
Status
Action Item (Who/What/Where/When/How) | Active Waiting Room Rounding: Assign a dedicated nurse to perform structured check-ins and reassessments on patients waiting.
Root Cause Addressed | Communication
Owner | Shelley Uhlir
Due Date | 2027-04-01
Status
Action Item (Who/What/Where/When/How)
Root Cause Addressed
Owner
Due Date
Status
Action Item (Who/What/Where/When/How)
Root Cause Addressed
Owner
Due Date
Status
Sustainment Plan
Action Item (Who/What/Where/When/How)
Owner
Frequency
Metric/Benchmark
Action Item (Who/What/Where/When/How)
Owner
Frequency
Metric/Benchmark
Action Item (Who/What/Where/When/How)
Owner
Frequency
Metric/Benchmark

## Results & Data Trending
Pending data points for measurment

## QAPI Completion Guide
QAPI Categories
QAPI Category Options | Definition | Examples
Patient Safety & Clinical Outcomes | Activities, measures, and improvement efforts focused on preventing harm to patients and improving measurable clinical outcomes through safe, effective, evidence‑based care. | healthcare-associated infection prevention, falls, pressure injuries, readmissions, hand hygiene
Patient Experience/Access/Care Coordiation | Efforts aimed at improving patients’ perceptions of care, access to services, communication, and coordination across care settings to ensure timely, seamless, and patient‑centered care. | patient satisfaction survey results, delays in care, care transtions, communication breakdown, missed follow up, complaints/grievances
Workforce Competence/Engagement/Alignment | Processes that support staff competency, engagement, alignment with organizational standards, and ability to reliably perform work in support of safe, high‑quality care. | onboarding effectiveness, staff engagement, role clarity, variation in adherence to standard work, staff competency validation, training gaps
Operational Effectiveness/Compliance/Resource Stewardship | Activities and improvement efforts focused on ensuring efficient, compliant, and reliable operations through appropriate use of resources, adherence to regulatory and policy requirements, and effective process design to support high‑quality care. | documentation accuracy/timeliness, resource utilizaation, throughput/capacity, audit findings, control failures, billing issues, waste reduction, cost-avoidance, technology/system reliablity issues
Primary Rationale
Primary Rationale Options | Definition | Example
High Risk | A process or outcome where failure is likely to cause significant patient harm, safety events, or regulatory risk, even if it occurs infrequently. | medication administration, infection prevention, surgery, restraints, blood transfusions.
High Volume | A process or service that occurs frequently or affects a large number of patients, increasing the likelihood that even small failures can impact many individuals. | hand hygiene, admission assessments, discharge processes, medication reconciliation.
Problem Prone | A process with a history of errors, performance variation, complaints, incidents, or lack of reliability, indicating a need for system‑level improvement. | repeated audit failures, recurring incident reports, fluctuating compliance rates.
Regulatory | A requirement that is mandated or directly referenced by CMS, accrediting bodies, or applicable laws, where non‑compliance may result in citations, penalties, or loss of reimbursement. | Conditions of Participation standards, patient rights, infection control, discharge planning.
Strategic | An issue that directly supports the organization’s strategic goals, quality priorities, or value‑based performance outcomes, even if current performance is acceptable. | CMS star ratings, value‑based purchasing measures, growth service lines, health equity initiatives.
Measures & Baseline Data
This section defines how performance will be measured, establishes current performance (baseline), and identifies the target for improvement. Measures must directly relate to the problem statement and improvement goal.
Data | Definition | Examples
Outcome Measure | Select a measure that reflects the impact of the process on patients, staff, or operations. | hand hygiene compliance rate, fall rate per 1,000 patient days, medication error rate, 30 day readmission rate, % of records meeting documentation standards
Outcome measures show whether risk was reduced or performance improved.
Baseline Performance | This is the most recent and reliable data available before actions were implemented | 64% January to August 2026
Include the timeframe
Baseline data establishes the comparison point for improvement
Target/Benchmark | This is the level of performance you are amining to reach. | Targets must be clear, measurable, and understandable
Expressed as percentages or rates (i.e. < 3 per 1,000)
Data Source | This is where the data comes from. | audit tools, incident reporting system, logs/trackers, observation tools
Data Collection Frequency | This is how often the data will be reviewed. | monthly, quarterly, each event
Data Owner | This is who is responsible for collecting and reporting the data. | Infection prevention, quality, nursing, finance, operations
Root Cause Analysis (RCA)
Root Cause Analysis (RCA) is a structured way to understand what in the system or process allowed a problem to occur, rather than focusing on individual actions or performance. An RCA may identify more than one root cause when appropriate. When this happens, each root cause must be addressed by a specific improvement action. The purpose of RCA is to move beyond explanation and ensure that identified system issues lead to practical, sustainable solutions that reduce the risk of recurrence.
RCA Method | Quick Steps | Example
5 Whys | Define the problem → Ask “Why?” → Answer → Ask “Why?” again → Repeat 3–5 times → Stop at a system or process cause you can act on (not individual behavior). | The Jefferson Memorial and The 5 Whys
Cause and Effect | Define the problem → List possible causes → Group causes by category → Ask “Which cause best explains the issue?” → Select system/process causes. | Cause and Effect (Fishbone Diagram)
Process Map | List the steps as they actually occur → Include handoffs and delays → Identify where the process breaks down → Note system or workflow gaps. | How To Use A Process Map
Root Cause Analysis focuses on systems and processes — not individual performance. A strong RCA identifies what in the workflow, design, environment, or system allowed the problem to occur, even if staff were trying to do the right thing.
Root Cause Analysis Library
Workflow & Process Design | Daily workflows did not reliably support the required process.
The process was not well integrated into routine work.
Workflow variation led to inconsistent performance.
The process required extra steps that were difficult to complete during busy care.
The process was not designed to function well during high workload or time pressure.
Standardization & Clarity | The process was not standardized across staff or shifts.
Expectations were not consistently reinforced during daily operations.
Roles and responsibilities within the process were unclear.
Key steps were interpreted differently across areas or staff.
Environment, Tools & Resources | Needed supplies or tools were not consistently available at the point of use.
Physical layout made the process harder to complete correctly.
Technology did not reliably support the intended workflow.
Visual cues or reminders were insufficient or inconsistent.
Communication & Handoffs | Communication breakdowns occurred during handoffs or transitions.
Information was not consistently shared across team members.
Process expectations were not clearly communicated at key points.
Follow‑up communication was inconsistent or delayed.
Monitoring, Feedback & Visiblity | Performance data was not consistently visible to staff.
Leaders lacked timely data to reinforce or course‑correct performance.
Feedback was delayed or inconsistent.
Performance trends were not routinely reviewed.
Leadership & Oversight | Oversight processes did not reliably support ongoing performance.
Accountability for the process was not clearly assigned.
Competing priorities limited consistent leadership reinforcement.
Monitoring was not embedded into routine leadership work.
Training & Competency (Use Carefully/Rarely- Only when tied to system gaps-not individual fault) | Training was not aligned with actual workflow conditions.
Training did not adequately prepare staff for real‑world scenarios.
Competency validation did not assess performance in practice.
Learning was not reinforced after initial training.
SMART Goal
A SMART Goal is a clearly defined improvement goal that specifies what will improve, by how much, and by when. SMART goals ensure QAPI projects are measurable, time‑bound, and focused on meaningful outcomes rather than activities alone. A strong SMART goal makes it easy to determine if improvement was achieved.
Specific | Clearly states what will change | Increase hand hygiene compliance
Measurable | Uses data to track improvement | From 64% to 100%
Achievable | Realistic given current resources and workflow
Relevant | Addresses a meaningful quality, safety, or compliance issue
Time-Bound | Includes a defined completion date | By 12/31/2026
Action Plan
An Action Plan describes what will be done to fix the system issue identified in the RCA and prevent it from happening again. Each action should clearly link back to a root cause and describe how the change will be carried out, who is responsible, and how success will be measured over time.
Plan-Do-Study-Act (PDSA)
Plan‑Do‑Study‑Act (PDSA) is the method used to test, adjust, and strengthen actions before moving to sustainment. Actions identified in the Action Plan are implemented, reviewed, and refined using PDSA cycles to ensure they achieve the desired outcome.
Plan | Identify what change will be tested and how success will be measured.
Do | Implement the action as planned.
Study | Review data and observations to determine what is working and what is not.
Act | Refine, expand, or adjust the action based on what was learned.
If an action is partially effective, it should not be stopped. Instead, the action is built upon or adjusted and retested through additional PDSA cycles. PDSA cycles are repeated as needed until the improvement goal is met and performance is stable. Once effectiveness is demonstrated, the action moves into the Sustainment Plan.
Sustainment Plan
Sustainment Plan describes how improvements will be maintained over time after an action has been shown to be effective. The sustainment plan identifies how the change will be built into routine operations, who is responsible for ongoing oversight, and how performance will continue to be monitored. The goal is to ensure gains are sustained and to quickly identify and address any drift from the improved process.

## Example
2027 QAPI
QAPI Project Identification
Department | Inpatient Nursing Unit- 4 East
QAPI Category | Patient Safety & Clinical Outcomes
Project Title | Improving Hand Hygiene Compliance
Executive Sponsor | Dr. Max Imumvalue
Project Lead (Name and Title) | Ima Tryhard, Unit Manager
Team Members | Ann A. Lytics, Will Washmore, Sandy Tizer, Holly Hygiene, Lottie Rinse, Foamy McClean
Oversight Committee | Quality Council
Review Frequency | Monthly
Problem Statement & Rationale
Problem Statement | Data from direct observational audits shows that hand hygiene performance is 64% compared to the hospital expectation of 100%, creating risk related to healthcare-associated infections and patient harm.
Primary Rationale | Problem-prone
Measures & Baseline Data
Outcome Measure | Hand Hygiene compliance measure
Baseline Performance | 64% January -August 2026
Target/Benchmark | 100%
Data Source | Standardized hand hygiene direct observation tool
Data Collection Frequency | Monthly
Data Owner | Infection Prevention Department
Root Cause Analysis
Finding | The root cause of absent or inadequate hand hygiene was that established hand hygiene processes were not reliably sustained over time in real‑world clinical workflows, which resulted from insufficient integration of hand hygiene into high‑acuity, time‑pressured care and a perception that hand hygiene slowed patient care.
SMART Goal
Goal | Increase hand hygiene compliance from 64% to 100% by 12/31/2027.
Action Plan/Interventions
Action Item | Standardize placement of hand sanitizer at point of care
Root Cause Addressed | Hand hygiene was hard to perform consistently during fast‑paced clinical care.
Owner | Facilities
Due Date | 2027-01-15
Status
Action Item | Standardize reinforcement education during daily huddles
Root Cause Addressed | Daily work demands limited consistent hand hygiene reinforcement.
Owner | Unit Manager/Supervisor
Due Date | 2027-06-01
Status
Action Item | Implement real‑time verbal feedback during observations
Root Cause Addressed | Hand hygiene performance was not consistently visible to leaders.
Owner | Infection Prevention Team/Manager
Due Date | 2027-04-01
Status
Action Item | Monthly compliance reports shared with unit leaders
Root Cause Addressed | Hand hygiene performance was not consistently visible to leaders.
Owner | Informaticist
Due Date | Ongoing
Status
Action Item
Root Cause Addressed
Owner
Due Date
Status
Sustainment Plan
Action Item
Owner
Frequency
Metric/Benchmark
Action Item
Owner
Frequency
Metric/Benchmark
Action Item
Owner
Frequency
Metric/Benchmark