## Financial Analysis 2027 QAPI
2027 QAPI
QAPI Project Identification
Department | Financial Analysis Dept 8550
QAPI Category | Workforce Competence/Engagement/Alignment
Project Title | Improving Departmental Annual Costing Review Process & Tracking
Executive Sponsor | Sonni Pinkerton - Director of Financial Analysis
Project Lead (Name and Title) | Adam Zibert - Senior Financial Analyst
Team Members | Grant Brand - Financial Analyst
Oversight Committee | Quality Council
Review Frequency | Quarterly
Problem Statemement & Rationale
Problem Statement | Allocations of labor, supplies and lab send-outs updates are not being kept up in a timely manner which creates a risk related to incorrect cost & profitabilty analyses which can impede good decision making by management based on those parameters.
Primary Rationale | Strategic
Measures & Baseline Data
Outcome Measure | % of Costing Parameters
Baseline Performance | 75% Completion Annually of Costing Parameters
Target/Benchmark | 100% Completion Annually
Data Source | Audits of CostFlex Costing Software, DNZ Emails & Annual Mgt Reviews
Data Collection Frequency | Quarterly
Data Owner | Adam Zibert, Sr. Financial Analyst
Root Cause Analysis
Finding | Lack of a standardized process results in a failure to update costing parameters in a timely manner.
SMART Goal
Goal | Improve the review process & frequency of costing parameters from 75% to 100% annually by December 31, 2027.
Action Plan/Interventions
Action Item (Who/What/Where/When/How) | Complete dedicated education time with staff as to the importance of accurate costing and how costing parameters are determined
Root Cause Addressed | Lack of Knowledge Transfer - Position changes within department
Owner | Sonni Pinkerton
Due Date | 1.15.27
Status
Action Item (Who/What/Where/When/How) | Outline New Quarterly Schedule of Departmental Annual Costing Review & Tracking System
Root Cause Addressed | Time Restraints and Inconsistent Tracking
Owner | Sonni Pinkerton
Due Date | 2.15.27
Status
Action Item (Who/What/Where/When/How) | Research Available Costing Tools in CostFlex
Root Cause Addressed | Identification of Unknown Available Tools
Owner | Adam Zibert
Due Date | 6.15.27
Status
Action Item (Who/What/Where/When/How) | Document Annual Costing Process, Definitions, Goals & Department Expectations
Root Cause Addressed | Incomplete / Out of Date Documentation
Owner | Sonni Pinkerton
Due Date | 2.15.27
Status
Action Item (Who/What/Where/When/How) | Use Tracking System to Identify Depts which have Parameters that Fluctuate More Frequently & Other Opportunites to Improve Costing. Once identified formulate plan to improve timliness of cost updates.
Root Cause Addressed | Out of Date Costing Parameters
Owner | Adam Zibert
Due Date | 12.31.27
Status
Sustainment Plan
Action Item (Who/What/Where/When/How)
Owner
Frequency
Metric/Benchmark
Action Item (Who/What/Where/When/How)
Owner
Frequency
Metric/Benchmark
Action Item (Who/What/Where/When/How)
Owner
Frequency
Metric/Benchmark